## EXEC tRACKER
STAGE | RUN TYPE | START | END | TEST DATE | STATUS | Dependencies/Comments | DEFECTS
SCRIPTING FOR BCC | NA | 2025-10-17 | 2025-10-20 |  | DONE |  | NA
SCRIPTING FOR DATA PREP | NA | 2025-10-17 | 2025-10-27 |  | DONE | * Only Immigration case templates are present in PERF | NA
* TP | [5 empty] | * Scripts to be updated for Tax templates as well after necessary templates are added in PERF
* Service Creation
* Merge
DATA PREP EXECUTION | NA | 2025-10-23 | 2025-11-04 |  | DONE | For all 20K Profiles, TP & Services | NA
EXECUTION #1 - Smoke test | STANDALONE | 2025-10-30 | 2025-10-31 |  | DONE | Restricted to 1 Client and 2000 records RESULTS shared | NA
EXECUTION #2 | STANDALONE | 2025-11-04 | 2025-11-04 |  | DONE | Completed with 5 Clients & 10K records - completed in ~5 hrs 20min (RESULTS shared) * Observed wait times between web jobs | BUG 1459621
EXECUTION #3 | INTEGRATED | 2025-11-12 | 2025-11-13 |  | DONE | Run with 1029U AP test run with 2K REC.
EXECUTION #4 | INTEGRATED | 2025-11-13 | 2025-11-14 |  | DONE | Run with 1544U test run & 6K REC
EXECUTION #5 | STANDALONE | 2025-11-14 | 2025-11-15 |  | DONE | STANDLONE GDC RUN with 20K REC for a baseline
EXECUTION #6 | INTEGRATED | 2025-11-17 | 2025-11-18 |  | DONE | Run with 1544U test run & 6K REC
EXECUTION #7 | INTEGRATED | TBD |  |  | YET TO START | Run with 2217U STRESS test run & 2K REC (Depending on above runs)
EXECUTION #8 | INTEGRATED | TBD |  |  | YET TO START | Run with 1544U test run & 2K REC (ENDURANCE) (Depending on above runs)
EXECUTION #9 | INTEGRATED | TBD |  |  | YET TO START | Run with 1544U test run & 20K REC (GOLD BUILD) (Depending on above runs)

## RUN LOG
SL.NO. | DATE OF EXECUTION | TYPE OF TEST | TEST | TIME TO COMPLETE PER EACH 2K FILE | WEB JOB 1 PROCESSING TIME | WEB JOB 2 PROCESSING TIME | WEB JOB 3 PROCESSING TIME | RETRY JOB PROCESSING TIME | AVG . TIME PER INPUT CASE (in sec)
All times in hh:mm:ss.mmm
1 | 2025-10-31 | STANDALONE | 1Client_2K REC | 1:49 | 0:05 | 1:10 | 0:26 | NA | 3.27
2 | 2025-11-04 | STANDALONE | 5 Clients_10K REC | 2:48 | 0:05 | 1:49 | 0:43 | 0:00 | 5
|  |  |  | 4:22 | 0:05 | 1:51 | 0:27 | 0:00 | 7.83
|  |  |  | 4:48 | 0:05 | 1:52 | 0:26 | 0:00 | 8.64
|  |  |  | 2:55 | 0:05 | 1:48 | 0:51 | 0:00 | 5.24
|  |  |  | 5:19 | 0:05 | 0:56 | 0:25 | 0:00 | 9.58
3 | 2025-11-12 | INTEGRATED | 1029UAP+2K REC | 1:30 | 0:05 | 0:53 | 0:24 | NA | 2.68
4 | 2025-11-13 | INTEGRATED | 1544UAP+6K REC | 3:55 | 0:05 | 1:22 | 0:25 | NA | 7.05
|  |  |  | 3:52 | 0:05 | 1:52 | 1:47 | NA | 6.96
|  |  |  | 3:53 | 0:05 | 1:52 | 1:47 | NA | 6.98
5 | 2025-11-14 | STANDALONE | 9 Clients_20K REC | 0:58 | 0:00 | 0:21 | 0:23 | NA | 1.74
|  |  |  | 3:14 | 0:00 | 0:21 | 0:23 | NA | 5.82
|  |  |  | 3:38 | 0:00 | 0:21 | 0:25 | NA | 6.55
|  |  |  | 4:01 | 0:00 | 0:22 | 0:24 | NA | 7.22
|  |  |  | 4:24 | 0:00 | 0:21 | 0:24 | NA | 7.92
|  |  |  | 2:00 | 0:00 | 0:21 | 0:23 | NA | 3.6
|  |  |  | 2:22 | 0:00 | 0:21 | 0:23 | NA | 4.25
|  |  |  | 2:42 | 0:00 | 0:21 | 0:23 | NA | 4.87
|  |  |  | 1:32 | 0:00 | 0:22 | 0:22 | NA | 2.76
|  |  |  | 1:10 | 0:00 | 0:23 | 0:23 | NA | 2.1
6 | 2025-11-18 | INTEGRATED | 1544UAP+6K REC | 1:42 | 0:00 | 0:39 | 0:53 | NA | 3.05
|  |  |  | 1:40 | 0:00 | 0:39 | 0:52 | NA | 3
|  |  |  | 2:00 | 0:00 | 0:19 | 0:20 | NA | 3.6
7 | 2025-11-20 | INTEGRATED | 1544UAP+9 Clients_20K REC | 5:27 | 0:00 | 0:39 | 1:38 | NA | 0:00
|  |  |  | 0:52 | 0:00 | 0:20 | 0:20 | NA | 0:00
|  |  |  | 5:25 | 0:00 | 0:19 | 1:38 | NA | 0:00
|  |  |  | 5:24 | 0:00 | 0:39 | 1:38 | NA | 0:00
|  |  |  | 2:01 | 0:00 | 0:39 | 0:56 | NA | 0:00
|  |  |  | 2:54 | 0:00 | 0:20 | 0:53 | NA | 0:00
|  |  |  | 1:59 | 0:00 | 0:39 | 0:56 | NA | 0:00
|  |  |  | 2:53 | 0:00 | 0:19 | 0:54 | NA | 0:00
|  |  |  | 3:42 | 0:00 | 0:41 | 0:50 | NA | 0:00
|  |  |  | 3:32 | 0:00 | 0:41 | 0:41 | NA | 0:00
8 | 2025-11-28 | INTEGRATED | 1544UAP+9 Clients_20K REC | 1:11 | 0:00 | 0:21 | 0:37 | NA | 0:00
|  |  |  | 3:09 | 0:00 | 0:22 | 0:29 | NA | 0:00
|  |  |  | 3:38 | 0:00 | 0:21 | 0:29 | NA | 0:00
|  |  |  | 5:04 | 0:00 | 0:22 | 0:29 | NA | 0:00
|  |  |  | 4:35 | 0:00 | 0:21 | 0:29 | NA | 0:00
|  |  |  | 4:05 | 0:00 | 0:22 | 0:29 | NA | 0:00
|  |  |  | 1:39 | 0:00 | 0:22 | 0:32 | NA | 0:00
|  |  |  | 5:30 | 0:00 | 0:22 | 0:29 | NA | 0:00
|  |  |  | 2:07 | 0:00 | 0:23 | 0:29 | NA | 0:00
|  |  |  | 2:35 | 0:00 | 0:23 | 0:29 | NA | 0:00
9 | 2025-12-08 | INTEGRATED | 1544UAP+9 Clients_20K REC | 0:49 | 0:00 | 0:17 | 0:19 | NA | 0:00
|  |  |  | 2:22 | 0:00 | 0:17 | 0:19 | NA | 0:00
|  |  |  | 3:00 | 0:00 | 0:10 | 0:19 | NA | 0:00
|  |  |  | 3:18 | 0:00 | 0:17 | 0:18 | NA | 0:00
|  |  |  | 3:36 | 0:00 | 0:18 | 0:19 | NA | 0:00
|  |  |  | 2:38 | 1:51 | 0:10 | 0:00 | NA | 0:00
|  |  |  | 1:02 | 0:00 | 0:18 | 0:19 | NA | 0:00
|  |  |  | 1:21 | 0:00 | 0:17 | 0:19 | NA | 0:00
|  |  |  | 1:57 | 0:00 | 0:19 | 0:18 | NA | 0:00
|  |  |  | 1:39 | 0:00 | 0:18 | 0:19 | NA | 0:00
10 | 2026-03-16 | AUTOMATED | Run_16Mar2026 | 01:29:35.213999 | 00:00:08.452999 | 00:40:32.726999 | 00:36:44.637000 | NA | 2.688
|  |  |  | 01:56:34.859999 | 00:00:05.599999 | 00:39:14.460000 | 00:28:44.395999 | NA | 3.497
|  |  |  | 01:53:21.789999 | 00:00:00.987000 | 00:00:08.449999 | 00:00:08.526999 | NA | 971.684
|  |  |  | 01:42:53.516999 | 00:00:01.062999 | 00:00:07.682999 | 00:00:08.307000 | NA | 881.931
|  |  |  | 01:27:15.899999 | 00:00:01.649999 | 00:00:07.043000 | 00:00:09.012999 | NA | 747.986
|  |  |  | 00:09:02.474000 | 00:00:01.199999 | 00:00:01.786000 | 00:00:10.173999 | NA | 77.496
|  |  |  | 00:13:16.832999 | 00:00:05.115999 | 00:00:04.564000 | 00:00:10.132999 | NA | 113.833
|  |  |  | 01:37:39.753999 | 00:00:01.227000 | 00:00:07.642999 | 00:00:08.856999 | NA | 837.108
|  |  |  | 01:11:31.063000 | 00:00:00.854000 | 00:00:07.160000 | 00:00:07.847000 | NA | 613.009
|  |  |  | 01:48:06.729999 | 00:00:00.933000 | 00:00:06.423000 | 00:00:07.963000 | NA | 926.676
|  |  |  | 01:32:28.216999 | 00:00:00.926000 | 00:00:06.932999 | 00:00:09.490000 | NA | 792.602
|  |  |  | 01:06:18.603999 | 00:00:00.956000 | 00:00:07.743000 | 00:00:09.369999 | NA | 568.372
|  |  |  | 00:14:15.113000 | 00:00:05.703000 | 00:00:05.919999 | 00:00:20.666000 | NA | 122.159
|  |  |  | 01:22:02.329999 | 00:00:00.990000 | 00:00:08.382999 | 00:00:07.996000 | NA | 703.19

## 5 Clients_10K REC
FILES (10K REC) | 1. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 (2K REC) | 2. CLIENT ID - 8c820a5e-74a7-43ff-a1a5-9f9d042dd0fb (2K REC) | 3. CLIENT ID - 6437a817-06f5-4f95-ab7d-964cf90c3f4c (2K REC) | 4. CLIENT ID - bcb25c9c-c1bd-42f3-b260-f37eefa8fcc7 (2K REC) | 5. CLIENT ID - fce0bb0b-a37a-445b-8213-064bfeb7d1f4 (2K REC)
STATUS | SUCCESSFUL | SUCCESSFUL | SUCCESSFUL | SUCCESSFUL | SUCCESSFUL
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:04 | 0:04 | 0:04 | 0:04 | 0:04
WEB JOB 1 Processing time | 0:05 | 0:05 | 0:05 | 0:05 | 0:05
WAIT TIME 1 (WJ2 - WJ1) -- > | 0:05 | 1:53 | 1:54 | 0:05 | 3:45
WEB JOB 2 Processing time | 1:49 | 1:51 | 1:52 | 1:48 | 0:56
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:01 | 0:00 | 0:27 | 0:02 | 0:05
WEB JOB 3 Processing time | 0:43 | 0:27 | 0:26 | 0:51 | 0:25
WAIT TIME 3 (WJ4 - WJ3) -- > | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
RETRY JOB Processing time | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
TOTAL PROCESSING TIME (hh:mm:ss.000) | 2:48 | 4:22 | 4:48 | 2:55 | 5:19
AVG. Time per input case | 5 sec per case | 7.83 sec per case | 8.638 | 5.2365 | 9.575

## 1Client_2K REC
Waiting Time
Processingd time
EndToEnd- completion | 1:49 | 0:08
Job1 | 0:05 | 0:03
Job2 | 1:10 | 0:05
Job3 | 0:26 | 0:00
JobGuid à | 00896F2D-351B-49BC-90DB-A04FDFA12ADF
JobStartDateTime à | 10/31/2025 20:51 UTC
STAGES | Job Step Name | Description | Job Definition StepStatusId | CreatedTimestamp
Bulk case create API invoke: | CREATE_JOB | Log Request to BP Request Header table and Create Job | 1 | 10/31/2025 20:52
Web job 1: | LOAD_TO_BLOB | GDC.CM_LoadData Webjob - Input file upload blob storage | 2 | 10/31/2025 20:55
| LOAD_TO_BLOB | GDC.CM_LoadData Webjob - Input file upload blob storage | 3 | 10/31/2025 20:55
| LOAD_TO_STG | GDC.CM_LoadData Webjob - Load data to staging tables | 2 | 10/31/2025 21:00
| LOAD_TO_STG | GDC.CM_LoadData Webjob - Load data to staging tables | 3 | 10/31/2025 21:00
Web job 2: | DATA_VALIDATE | GDC.CM_ValidateData. Validate the case creation request received | 2 | 10/31/2025 21:05
| DATA_VALIDATE | GDC.CM_ValidateData. Validate the case creation request received | 3 | 10/31/2025 22:14
Web job 3: | CREATE_CASE | GDC.CM_CreateCase.Create Cases at EYMP - Case Created Successfully | 2 | 10/31/2025 22:15
| CREATE_REPORT | GDC.CM_CreateCase.Create Report from Staging table as Json | 2 | 10/31/2025 22:40
| CREATE_REPORT | GDC.CM_CreateCase.Create Report from Staging table as Json | 12 | 10/31/2025 22:40
| CREATE_REPORT | GDC.CM_CreateCase.Create Report from Staging table as Excel | 2 | 10/31/2025 22:40
| CREATE_REPORT | GDC.CM_CreateCase.Create Report from Staging table as Excel | 12 | 10/31/2025 22:40
Retry web job 3: | CREATE_CASE | GDC.CM_CreateCase.Create Cases at EYMP - Case Created Successfully | 4 | 10/31/2025 22:40
| CREATE_CASE | GDC.CM_CreateCase.Create Cases at EYMP - Case Created Successfully | 2 | 10/31/2025 22:40
| CREATE_REPORT | GDC.CM_CreateCase.Create Report from Staging table as Json | 2 | 10/31/2025 22:40
| CREATE_REPORT | GDC.CM_CreateCase.Create Report from Staging table as Json | 12 | 10/31/2025 22:40
| CREATE_REPORT | GDC.CM_CreateCase.Create Report from Staging table as Excel | 2 | 10/31/2025 22:40
| CREATE_REPORT | GDC.CM_CreateCase.Create Report from Staging table as Excel | 12 | 10/31/2025 22:40
Final status | CREATE_CASE | GDC.CM_CreateCase.Create Cases at EYMP - Case Created Successfully | 3 | 10/31/2025 22:40
OVERALL BATCH PROCESSING TIME | Final status time - Job start time | 22:40-20:51= 1hour 49 min
| Time per input case | 3.27 sec per case

## 1029UAP+2K
| GDC 2k File Bulk Case Creation Isolated Execution - 31st Oct Job GUID - 00896F2D-351B-49BC-90DB-A04FDFA12ADF | 1029U AP Full Load + GDC 2k File Bulk Case Creation Execution - 12th Nov Job GUID - 12c04481-c70b-4bc5-b16c-80493d08b363
FILES --> | CLIENT ID - 6437a817-06f5-4f95-ab7d-964cf90c3f4c | CLIENT ID - fce0bb0b-a37a-445b-8213-064bfeb7d1f4
STATUS | SUCCESSFUL | SUCCESSFUL
CREATE JOB >>
WAIT TIME | 0:03 | 0:00
WEB JOB 1 | 0:05 | 0:05
WAIT TIME | 0:05 | 0:05
WEB JOB 2 | 1:10 | 0:53
WAIT TIME | 0:00 | 0:02
WEB JOB 3 | 0:26 | 0:24
WAIT TIME | 0:00
RETRY JOB | 0:00
TOTAL PROCESSING TIME (hh:mm:ss) | 1:49 | 1:30
AVG. Time per input case | 3.26 sec | 2.68 sec

## 1544APUsers+6KBulkCase_14thNov
FILES (6K REC) | 1. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 JOB GUID - 9fe66383-c4e1-45f8-99dc-73730125e919 (2K REC) | 2. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 JOB GUID - 9ac8dddd-0ad2-4a1f-b4ea-5d4e2b9f4d2d (2K REC) | 3. CLIENT ID - fce0bb0b-a37a-445b-8213-064bfeb7d1f4 JOB GUID - 6b0d356c-3daa-4f4b-aff7-a3a977288bfd (2K REC)
STATUS | Job Partially Succeeded (1999/2000 processed) | Paritally succeeded (1572/2000 processed) | Paritally succeeded (1569/2000 processed)
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:04 | 0:00 | 0:01
WEB JOB 1 Processing time | 0:05 | 0:05 | 0:05
WAIT TIME 1 (WJ2 - WJ1) -- > | 1:32 | 0:05 | 0:05
WEB JOB 2 Processing time | 1:22 | 1:52 | 1:52
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:28 | 0:03 | 0:03
WEB JOB 3 Processing time | 0:25 | 1:47 | 1:47
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 3:55 | 3:52 | 3:53
AVG. Time per input case | 7.05 sec | 6.96 sec | 6.98 sec

## Standalone_9Clients_20K Rec
FILES (20K REC) | 1. CLIENT ID - fce0bb0b-a37a-445b-8213-064bfeb7d1f4 JOB GUID - 80acb2e0-597a-4c36-9d48-f74b064d1b5a (2K REC) | 2. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 JOB GUID - b5b7e2a2-2ce4-49be-88d1-2a11513e9bac (2K REC) | 3. CLIENT ID - 8c820a5e-74a7-43ff-a1a5-9f9d042dd0fb JOB GUID - d448ddf2-602f-4d69-b24e-befefa710a5e (2K REC) | 4. CLIENT ID - bcb25c9c-c1bd-42f3-b260-f37eefa8fcc7 JOB GUID - 042bd359-ab5b-4844-8b95-8287570a35db (2K REC) | 5. CLIENT ID - e0cc7d72-76ac-4cff-b407-21138dea2dbb JOB GUID - d632e970-b7b6-42dd-861e-82916e455963 (2K REC) | 6. CLIENT ID - cfec799a-1260-4098-840e-cbf3a7c6f6a3 JOB GUID - 46731ef3-66d8-4569-8698-2d3ab25fe903 (2K REC) | 7. CLIENT ID - 69ef852b-0fb3-4baa-8329-29ba4be371cb JOB GUID - 3b654588-def8-4e90-98d3-9369072d6ef1 (2K REC) | 8. CLIENT ID - c9099546-2737-4f7a-bd06-c4d4e8afbd1e JOB GUID - af317b97-e351-4490-bd57-283460a034de (2K REC) | 9. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - b793e26c-1f45-4b67-838e-43679e3060d7 (2K REC) | 9. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - 4386a5d9-283f-460d-b1e7-59f3f98adec6 (2K REC)
STATUS | Job Successfully Completed | Job Successfully Completed | Job Successfully Completed | Job Successfully Completed | Job Successfully Completed | Job Successfully Completed | Job Successfully Completed | Job Successfully Completed | Job Successfully Completed | Job Successfully Completed
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:05 | 0:04 | 0:03 | 0:01 | 0:00 | 0:04 | 0:02 | 0:00 | 0:04 | 0:03
WEB JOB 1 Processing time | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 0:05 | 2:14 | 2:35 | 2:56 | 3:18 | 1:06 | 1:27 | 1:48 | 0:38 | 0:16
WEB JOB 2 Processing time | 0:21 | 0:21 | 0:21 | 0:22 | 0:21 | 0:21 | 0:21 | 0:21 | 0:22 | 0:23
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:04 | 0:12 | 0:14 | 0:17 | 0:20 | 0:06 | 0:08 | 0:10 | 0:05 | 0:05
WEB JOB 3 Processing time | 0:23 | 0:23 | 0:25 | 0:24 | 0:24 | 0:23 | 0:23 | 0:23 | 0:22 | 0:23
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 0:58 | 3:14 | 3:38 | 4:01 | 4:24 | 2:00 | 2:22 | 2:42 | 1:32 | 1:10
AVG. Time per input case | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00

## 1544APUsers+6KBulkCase_18thNov
FILES (6K REC) | 1. CLIENT ID - FCE0BB0B-A37A-445B-8213-064BFEB7D1F4 JOB GUID - 62909624-cecf-4bfe-b83d-eab1cec99b51 (2K REC) | 2. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 JOB GUID - cd2a179d-9335-47d2-a833-395964ac463c (2K REC) | 3. CLIENT ID - 8c820a5e-74a7-43ff-a1a5-9f9d042dd0fb JOB GUID - 1ad807e6-abeb-462a-b835-d1c5d768d1dc (2K REC)
STATUS | Job Partially Succeeded (1947/2000 processed) | Paritally succeeded (1920/2000 processed) | Job Successfully Completed
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:04 | 0:03 | 0:02
WEB JOB 1 Processing time | 0:00 | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 0:05 | 0:05 | 0:44
WEB JOB 2 Processing time | 0:39 | 0:39 | 0:19
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:01 | 0:01 | 0:34
WEB JOB 3 Processing time | 0:53 | 0:52 | 0:20
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 1:42 | 1:40 | 2:00
AVG. Time per input case | 3.05 sec | 3 sec | 3.6 sec

## 1544APUsers_20KBulkCase_20thNov
FILES (20K REC) | 1. CLIENT ID - fce0bb0b-a37a-445b-8213-064bfeb7d1f4 JOB GUID - df890fe2-9ab0-4773-b8b2-a915c4593c2b (2K REC) | 2. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 JOB GUID - 1c8f3691-5f8d-4a16-adee-3b53708ea3b9 (2K REC) | 3. CLIENT ID - 8c820a5e-74a7-43ff-a1a5-9f9d042dd0fb JOB GUID - c38c7087-4ec4-4b35-9bba-f387cc195c10 (2K REC) | 4. CLIENT ID - bcb25c9c-c1bd-42f3-b260-f37eefa8fcc7 JOB GUID - 3597ce89-b8ae-4eab-b333-2fd4f54dd671 (2K REC) | 5. CLIENT ID - e0cc7d72-76ac-4cff-b407-21138dea2dbb JOB GUID - 1859a61f-0af1-499f-b4cd-5d6587209ea7 (2K REC) | 6. CLIENT ID - cfec799a-1260-4098-840e-cbf3a7c6f6a3 JOB GUID - dc958244-2dd4-4292-807b-7706a3741a97 (2K REC) | 7. CLIENT ID - 69ef852b-0fb3-4baa-8329-29ba4be371cb JOB GUID - d28eac5e-f65a-49d0-8b43-b32af3812a73 (2K REC) | 8. CLIENT ID - c9099546-2737-4f7a-bd06-c4d4e8afbd1e JOB GUID - 928d6b1f-50a5-4227-917b-396994db1408 (2K REC) | 9. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - 0f245fbf-9047-4fd7-97d9-4c3a7c3dadce (2K REC) | 9. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - 07dbab8d-1e4e-4b1c-b7eb-0e18ab131c39 (2K REC)
STATUS
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:03 | 0:02 | 0:01 | 0:00 | 0:04 | 0:04 | 0:03 | 0:02 | 0:01 | 0:01
WEB JOB 1 Processing time | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 2:24 | 0:05 | 3:03 | 2:24 | 0:20 | 0:59 | 0:20 | 1:19 | 1:38 | 1:38
WEB JOB 2 Processing time | 0:39 | 0:20 | 0:19 | 0:39 | 0:39 | 0:20 | 0:39 | 0:19 | 0:41 | 0:41
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:43 | 0:05 | 0:24 | 0:43 | 0:01 | 0:38 | 0:01 | 0:18 | 0:31 | 0:31
WEB JOB 3 Processing time | 1:38 | 0:20 | 1:38 | 1:38 | 0:56 | 0:53 | 0:56 | 0:54 | 0:50 | 0:41
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 5:27 | 0:52 | 5:25 | 5:24 | 2:01 | 2:54 | 1:59 | 2:53 | 3:42 | 3:32
AVG. Time per input case | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
7 Records Triggered in Every 5 Mins | WAIT TIME 0 (START - WJ1) -- > | WEB JOB 1 Processing time | WAIT TIME 1 (WJ2 - WJ1) -- > | WEB JOB 2 Processing time | WAIT TIME 2 (WJ3 - WJ2) -- > | WEB JOB 3 Processing time | Total Processing Time | Time/Case Creation
Iteration 1 | 0:05 | 0:00 | 0:14 | 0:00 | 0:01 | 0:00 | 0:20 | 0:03
Iteration 2 | 0:03 | 0:00 | 1:19 | 0:00 | 0:37 | 0:01 | 2:00 | 0:17
Iteration 3 | 0:00 | 0:00 | 0:24 | 0:00 | 0:01 | 0:00 | 0:26 | 0:04
Iteration 4 | 0:02 | 0:00 | 0:05 | 0:00 | 0:05 | 0:01 | 0:12 | 0:02
Iteration 5 | 0:01 | 0:00 | 0:34 | 0:00 | 0:00 | 0:00 | 0:36 | 0:05
Iteration 6 | 0:04 | 0:00 | 0:05 | 0:00 | 0:05 | 0:00 | 0:14 | 0:02
Iteration 7 | 0:04 | 0:00 | 0:05 | 0:00 | 0:05 | 0:01 | 0:15 | 0:02
Iteration 8 | 0:01 | 0:00 | 0:00 | 0:00 | 0:05 | 0:01 | 0:07 | 0:01
Iteration 9 | 0:02 | 0:00 | 0:10 | 0:00 | 0:04 | 0:01 | 0:18 | 0:03
Iteration 10 | 0:04 | 0:00 | 0:00 | 0:00 | 0:05 | 0:01 | 0:09 | 0:01
Iteration 11 | 0:04 | 0:00 | 0:09 | 0:00 | 0:01 | 0:01 | 0:15 | 0:02
Iteration 12 | 0:04 | 0:00 | 0:05 | 0:00 | 0:05 | 0:01 | 0:15 | 0:02
Iteration 13 | 0:01 | 0:00 | 0:29 | 0:00 | 0:01 | 0:00 | 0:31 | 0:04

## 1544APUsers_20KBulkCase_28thNov
FILES (20K REC) | 1. CLIENT ID - fce0bb0b-a37a-445b-8213-064bfeb7d1f4 JOB GUID - e5e6b0fe-a470-4f5f-8e6c-a4178a669d23 (2K REC) | 2. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 JOB GUID - 0f3696c5-7fde-4589-a915-6a51a3ee3013 | 3. CLIENT ID - 8c820a5e-74a7-43ff-a1a5-9f9d042dd0fb JOB GUID - 08e7ee29-92ea-42c1-a3b3-a8db92d64597 (2K REC) | 4. CLIENT ID - bcb25c9c-c1bd-42f3-b260-f37eefa8fcc7 JOB GUID - 819fa0fb-8c7c-49e7-9bcd-4a3f15254bce (2K REC) | 5. CLIENT ID - e0cc7d72-76ac-4cff-b407-21138dea2dbb JOB GUID - c9766928-209e-49ae-928a-190b7887b628 (2K REC) | 6. CLIENT ID - cfec799a-1260-4098-840e-cbf3a7c6f6a3 JOB GUID -4f79122b-805a-403b-b704-346b5b3b9763 (2K REC) | 7. CLIENT ID - 69ef852b-0fb3-4baa-8329-29ba4be371cb JOB GUID - 42e37115-4aef-409f-8db0-3f9e36b2d5cc (2K REC) | 8. CLIENT ID - c9099546-2737-4f7a-bd06-c4d4e8afbd1e JOB GUID - 3a96563b-5f12-49c5-bc6e-9e5591d53ee2 (2K REC) | 9. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - 54d2753f-7b4b-4af4-8cde-0563e338a096 (2K REC) | 9. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID -027c21a2-8044-49a2-8502-9313819c995b (2K REC)
STATUS
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:03 | 0:02 | 0:01 | 0:00 | 0:04 | 0:04 | 0:03 | 0:02 | 0:01 | 0:01
WEB JOB 1 Processing time | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 2:24 | 0:05 | 3:03 | 2:24 | 0:20 | 0:59 | 0:20 | 1:19 | 1:38 | 1:38
WEB JOB 2 Processing time | 0:39 | 0:20 | 0:19 | 0:39 | 0:39 | 0:20 | 0:39 | 0:19 | 0:41 | 0:41
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:43 | 0:05 | 0:24 | 0:43 | 0:01 | 0:38 | 0:01 | 0:18 | 0:31 | 0:31
WEB JOB 3 Processing time | 1:38 | 0:20 | 1:38 | 1:38 | 0:56 | 0:53 | 0:56 | 0:54 | 0:50 | 0:41
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 5:27 | 0:52 | 5:25 | 5:24 | 2:01 | 2:54 | 1:59 | 2:53 | 3:42 | 3:32
AVG. Time per input case | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
7 Records Triggered in Every 5 Mins | WAIT TIME 0 (START - WJ1) -- > | WEB JOB 1 Processing time | WAIT TIME 1 (WJ2 - WJ1) -- > | WEB JOB 2 Processing time | WAIT TIME 2 (WJ3 - WJ2) -- > | WEB JOB 3 Processing time | Total Processing Time | Time/Case Creation
Iteration 1 | 0:05 | 0:00 | 0:14 | 0:00 | 0:01 | 0:00 | 0:20 | 0:03
Iteration 2 | 0:03 | 0:00 | 1:19 | 0:00 | 0:37 | 0:01 | 2:00 | 0:17
Iteration 3 | 0:00 | 0:00 | 0:24 | 0:00 | 0:01 | 0:00 | 0:26 | 0:04
Iteration 4 | 0:02 | 0:00 | 0:05 | 0:00 | 0:05 | 0:01 | 0:12 | 0:02
Iteration 5 | 0:01 | 0:00 | 0:34 | 0:00 | 0:00 | 0:00 | 0:36 | 0:05
Iteration 6 | 0:04 | 0:00 | 0:05 | 0:00 | 0:05 | 0:00 | 0:14 | 0:02
Iteration 7 | 0:04 | 0:00 | 0:05 | 0:00 | 0:05 | 0:01 | 0:15 | 0:02
Iteration 8 | 0:01 | 0:00 | 0:00 | 0:00 | 0:05 | 0:01 | 0:07 | 0:01
Iteration 9 | 0:02 | 0:00 | 0:10 | 0:00 | 0:04 | 0:01 | 0:18 | 0:03
Iteration 10 | 0:04 | 0:00 | 0:00 | 0:00 | 0:05 | 0:01 | 0:09 | 0:01
Iteration 11 | 0:04 | 0:00 | 0:09 | 0:00 | 0:01 | 0:01 | 0:15 | 0:02
Iteration 12 | 0:04 | 0:00 | 0:05 | 0:00 | 0:05 | 0:01 | 0:15 | 0:02
Iteration 13 | 0:01 | 0:00 | 0:29 | 0:00 | 0:01 | 0:00 | 0:31 | 0:04

## 1544U_GBTest
FILES (20K REC) | e5e6b0fe-a470-4f5f-8e6c-a4178a669d23 | 0f3696c5-7fde-4589-a915-6a51a3ee3013 | 08e7ee29-92ea-42c1-a3b3-a8db92d64597 | 819fa0fb-8c7c-49e7-9bcd-4a3f15254bce | c9766928-209e-49ae-928a-190b7887b628 | 4f79122b-805a-403b-b704-346b5b3b9763 | 42e37115-4aef-409f-8db0-3f9e36b2d5cc | 3a96563b-5f12-49c5-bc6e-9e5591d53ee2 | 54d2753f-7b4b-4af4-8cde-0563e338a096 | 027c21a2-8044-49a2-8502-9313819c995b
STATUS | Job partially succeeded (1972/2000) | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job partially succeeded (1981/2000) | Job partially succeeded (1998/2000) | Job successfully completed | Job successfully completed
CREATE JOB >>
WAIT TIME 0 (START - WJ1) -- > | 0:04 | 0:03 | 0:02 | 0:01 | 0:01 | 0:00 | 0:04 | 0:04 | 0:03 | 0:03
WEB JOB 1 Processing time | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 0:05 | 1:55 | 2:40 | 2:18 | 3:23 | 3:01 | 0:21 | 0:43 | 1:05 | 1:28
WEB JOB 2 Processing time | 0:21 | 0:22 | 0:21 | 0:22 | 0:21 | 0:22 | 0:22 | 0:22 | 0:23 | 0:23
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:05 | 0:20 | 0:06 | 1:54 | 0:20 | 0:13 | 0:20 | 3:53 | 0:07 | 0:13
WEB JOB 3 Processing time | 0:37 | 0:29 | 0:29 | 0:29 | 0:29 | 0:29 | 0:32 | 0:29 | 0:29 | 0:29
WAIT TIME 3 (WJ4 - WJ3) -- > | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
RETRY JOB Processing time | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
TOTAL PROCESSING TIME (hh:mm:ss.000) | 1:11 | 3:09 | 3:38 | 5:04 | 4:35 | 4:05 | 1:39 | 5:30 | 2:07 | 2:35
AVG. Time per input case | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
7 DATA FILES | JobId:117 | JobId:133 | JobId:135 | JobId:115 | JobId:119 | JobId:132 | JobId:134 | JobId:131 | JobId:118 | JobId:137 | JobId:136 | JobId:116 | JobId:122
JobRequest | 20:26 | 20:59 | 21:10 | 20:15 | 20:37 | 20:54 | 21:04 | 20:48 | 20:32 | 21:21 | 21:15 | 20:21 | 20:43
Waitingtime | 0:04 | 0:01 | 0:00 | 0:05 | 0:03 | 0:02 | 0:01 | 0:02 | 0:03 | 0:04 | 0:05 | 0:04 | 0:02
WebJob1 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
Waitingtime | 0:05 | 0:11 | 0:01 | 0:05 | 0:05 | 0:16 | 0:06 | 1:51 | 0:00 | 0:08 | 0:13 | 0:00 | 2:18
WebJob2 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
Waitingtime | 0:05 | 0:04 | 0:05 | 0:05 | 0:05 | 0:04 | 0:05 | 0:13 | 0:05 | 0:20 | 0:19 | 0:05 | 0:20
WebJob3 | 0:00 | 0:17 | 0:06 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
OverAll Waittime | 0:14 | 0:16 | 0:06 | 0:15 | 0:13 | 0:21 | 0:11 | 2:06 | 0:08 | 0:32 | 0:37 | 0:09 | 2:40
Execution time | 0:00 | 0:17 | 0:06 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
TOTAL PROCESSING TIME (hh:mm:ss.000) | 0:14 | 0:33 | 0:12 | 0:15 | 0:13 | 0:22 | 0:11 | 2:06 | 0:08 | 0:32 | 0:38 | 0:10 | 2:40
AVG. Time per input case
Client ID | Job GUID | STATUS 20K
fce0bb0b-a37a-445b-8213-064bfeb7d1f4 | e5e6b0fe-a470-4f5f-8e6c-a4178a669d23 | Job partially succeeded | (1972/2000)
4ce60165-4071-4dc8-a29b-9f0ae382ed26 | 0f3696c5-7fde-4589-a915-6a51a3ee3013 | Job successfully completed
8c820a5e-74a7-43ff-a1a5-9f9d042dd0fb | 08e7ee29-92ea-42c1-a3b3-a8db92d64597 | Job successfully completed
bcb25c9c-c1bd-42f3-b260-f37eefa8fcc7 | 819fa0fb-8c7c-49e7-9bcd-4a3f15254bce | Job successfully completed
e0cc7d72-76ac-4cff-b407-21138dea2dbb | c9766928-209e-49ae-928a-190b7887b628 | Job successfully completed
cfec799a-1260-4098-840e-cbf3a7c6f6a3 | 4f79122b-805a-403b-b704-346b5b3b9763 | Job successfully completed
69ef852b-0fb3-4baa-8329-29ba4be371cb | 42e37115-4aef-409f-8db0-3f9e36b2d5cc | Job Partially Succeeded | (1981/2000)
c9099546-2737-4f7a-bd06-c4d4e8afbd1e | 3a96563b-5f12-49c5-bc6e-9e5591d53ee2 | Job Partially Succeeded | (1998/2000)
6437a817-06f5-4f95-ab7d-964cf90c3f4c | 54d2753f-7b4b-4af4-8cde-0563e338a096 | Job successfully completed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | 027c21a2-8044-49a2-8502-9313819c995b | Job successfully completed
Client ID | Job GUID-7 data files | STATUS 7 data
6437a817-06f5-4f95-ab7d-964cf90c3f4c | 08f6a11a-1fcb-40bf-aa9d-2a38d20224c3 | Job Partially Succeeded | 4/7 processed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | 1b5059a0-9db7-4d75-bcd6-bd7488e3fc94 | Job Successfully Completed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | 218de142-8573-4fc2-af86-0a0b313ae1f7 | Job Successfully Completed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | 37c21d2f-2b29-4314-9da9-0dc6ffe523e7 | Job Partially Succeeded | 3/7 processed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | 57118d9c-a502-4c6d-8624-aeedce2126a4 | Job Successfully Completed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | 59e64bcb-edd6-4aba-acd4-2a5c9dc2f58b | Job Successfully Completed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | 72cc72e7-df24-4c28-baad-a55ea3ef943b | Job Successfully Completed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | a18acc9f-1bd8-42e9-8e62-12822e92ca08 | Job Successfully Completed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | a2f93316-e163-4797-82b1-8809ffcc41c9 | Job Partially Succeeded | 4/7 processed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | a5701676-7001-4069-922e-22742f2f6fc2 | Job Successfully Completed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | b0ffc442-9eff-4fe7-92b9-9198c6a302d7 | Job Successfully Completed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | d9df8782-b81d-4331-af18-35c7e5ea55b5 | Job Partially Succeeded | 3/7 processed
6437a817-06f5-4f95-ab7d-964cf90c3f4c | e31d3338-78ee-4bfa-9408-0c9450ca3e91 | Job Successfully Completed

## 1544U_GBTest_LAPAutoscale_08Dec
FILES (20K REC) | 1. CLIENT ID - fce0bb0b-a37a-445b-8213-064bfeb7d1f4 JOB GUID - 4d0a84be-fdce-43b9-8e34-a8d18864066a (2K REC) | 2. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 JOB GUID - 1b8faa40-1e3a-44ba-9107-351eb25e7fef (2K REC) | 3. CLIENT ID - 8c820a5e-74a7-43ff-a1a5-9f9d042dd0fb JOB GUID - 7c9120b0-b456-48e4-ba5f-bad45c954122 (2K REC) | 4. CLIENT ID - bcb25c9c-c1bd-42f3-b260-f37eefa8fcc7 JOB GUID - 8b7fa47d-4cbb-45a2-86be-fcb98040f2a6 (2K REC) | 5. CLIENT ID - e0cc7d72-76ac-4cff-b407-21138dea2dbb JOB GUID - 6520540c-249e-4017-b37a-c45ca1651786 (2K REC) | 6. CLIENT ID - cfec799a-1260-4098-840e-cbf3a7c6f6a3 JOB GUID - fb0e9a91-3cfd-4d13-99a7-6bc7a0e5f110 (2K REC) | 7. CLIENT ID - 69ef852b-0fb3-4baa-8329-29ba4be371cb JOB GUID - e4c92cee-926b-4441-8c35-b8a7b6902804 (2K REC) | 8. CLIENT ID - c9099546-2737-4f7a-bd06-c4d4e8afbd1e JOB GUID - b515ad3b-0363-4ba2-ac38-93e66d360bdb (2K REC) | 9. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - bdaee162-824e-4cf9-931b-ffd63fdb697a (2K REC) | 9. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - d9cc727a-20ad-4951-8a76-0514da63b2d7 (2K REC)
STATUS | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job partially succeeded (1998/2000) | Job successfully completed | Job successfully completed | Job successfully completed
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:05 | 0:04 | 0:03 | 0:03 | 0:02 | 0:00 | 0:04 | 0:03 | 0:03 | 0:02
WEB JOB 1 Processing time | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 1:51 | 0:00 | 0:00 | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 0:04 | 1:34 | 2:09 | 2:27 | 2:45 | 0:17 | 0:17 | 0:35 | 1:11 | 0:52
WEB JOB 2 Processing time | 0:17 | 0:17 | 0:10 | 0:17 | 0:18 | 0:10 | 0:18 | 0:17 | 0:19 | 0:18
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:03 | 0:08 | 0:10 | 0:12 | 0:13 | 0:19 | 0:04 | 0:06 | 0:07 | 0:07
WEB JOB 3 Processing time | 0:19 | 0:19 | 0:19 | 0:18 | 0:19 | 0:00 | 0:19 | 0:19 | 0:18 | 0:19
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 0:49 | 2:22 | 3:00 | 3:18 | 3:36 | 2:38 | 1:02 | 1:21 | 1:57 | 1:39
AVG. Time per input case | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
7 Records Triggered in Every 5 Mins | WAIT TIME 0 (START - WJ1) -- > | WEB JOB 1 Processing time | WAIT TIME 1 (WJ2 - WJ1) -- > | WEB JOB 2 Processing time | WAIT TIME 2 (WJ3 - WJ2) -- > | WEB JOB 3 Processing time | Total Processing Time | Time/Case Creation
Iteration 1 | 0:04 | 0:00 | 0:07 | 0:00 | 0:03 | 0:00 | 0:14 | 0:02
Iteration 2 | 0:03 | 0:00 | 0:10 | 0:00 | 0:04 | 0:00 | 0:17 | 0:02
Iteration 3 | 0:03 | 0:00 | 0:15 | 0:00 | 0:04 | 0:00 | 0:23 | 0:03
Iteration 4 | 0:01 | 0:00 | 0:07 | 0:00 | 0:06 | 0:00 | 0:15 | 0:02
Iteration 5 | 0:03 | 0:00 | 0:05 | 0:00 | 0:04 | 0:00 | 0:12 | 0:02
Iteration 6 | 0:05 | 0:00 | 0:12 | 0:00 | 0:03 | 0:00 | 0:20 | 0:03
Iteration 7 | 0:02 | 0:00 | 0:13 | 0:00 | 0:06 | 0:00 | 0:20 | 0:03
Iteration 8 | 0:02 | 0:00 | 0:00 | 0:00 | 0:04 | 0:00 | 0:07 | 0:01
Iteration 9 | 0:04 | 0:00 | 0:02 | 0:00 | 0:03 | 0:00 | 0:09 | 0:01
Iteration 10 | 0:01 | 0:00 | 0:05 | 0:00 | 0:05 | 0:00 | 0:11 | 0:02
Iteration 11 | 0:02 | 0:00 | 0:05 | 0:00 | 0:05 | 0:00 | 0:12 | 0:02
Iteration 12 | 0:01 | 0:00 | 0:00 | 0:00 | 0:05 | 0:00 | 0:07 | 0:01

## R18_Test#1
Client ID | JOB GUID
6437A817-06F5-4F95-AB7D-964CF90C3F4C | 4eda46c2-486f-42f0-a96a-7cfe857b9c53 Job Successfully Completed
6437A817-06F5-4F95-AB7D-964CF90C3F4C | ded124f9-79d2-4900-a5d9-6fd01bc642f1 Job Successfully Completed
FCE0BB0B-A37A-445B-8213-064BFEB7D1F4 | bcf2a698-9e68-4958-9e07-d8c4372e7408 Job Successfully Completed
4CE60165-4071-4DC8-A29B-9F0AE382ED26 | 76f72634-70e6-491b-ad61-5d0b5d39f19f Job Successfully Completed
8c820a5e-74a7-43ff-a1a5-9f9d042dd0fb | 25091fde-2aa5-4f94-81fa-3a926dac26dd Job Successfully Completed
bcb25c9c-c1bd-42f3-b260-f37eefa8fcc7 | 6ccb048b-f26c-45df-8fc8-21dcc54dd632 Job Successfully Completed
e0cc7d72-76ac-4cff-b407-21138dea2dbb | f24d48e8-aa43-4f9c-91b7-9512f94749b1 Job Successfully Completed
cfec799a-1260-4098-840e-cbf3a7c6f6a3 | 5a6ebeca-0663-4659-9aaf-c4382533f394 Job Successfully Completed
69ef852b-0fb3-4baa-8329-29ba4be371cb | 264d33ef-8d64-4303-932f-7f3ee7ecf640 Job Successfully Completed
c9099546-2737-4f7a-bd06-c4d4e8afbd1e | 34bed8af-297b-4755-b551-f8018dcc7f4a Job Successfully Completed
FILES (20K REC) | 1. CLIENT ID - fce0bb0b-a37a-445b-8213-064bfeb7d1f4 JOB GUID - 4d0a84be-fdce-43b9-8e34-a8d18864066a (2K REC) | 2. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 JOB GUID - 1b8faa40-1e3a-44ba-9107-351eb25e7fef (2K REC) | 3. CLIENT ID - 8c820a5e-74a7-43ff-a1a5-9f9d042dd0fb JOB GUID - 7c9120b0-b456-48e4-ba5f-bad45c954122 (2K REC) | 4. CLIENT ID - bcb25c9c-c1bd-42f3-b260-f37eefa8fcc7 JOB GUID - 8b7fa47d-4cbb-45a2-86be-fcb98040f2a6 (2K REC) | 5. CLIENT ID - e0cc7d72-76ac-4cff-b407-21138dea2dbb JOB GUID - 6520540c-249e-4017-b37a-c45ca1651786 (2K REC) | 6. CLIENT ID - cfec799a-1260-4098-840e-cbf3a7c6f6a3 JOB GUID - fb0e9a91-3cfd-4d13-99a7-6bc7a0e5f110 (2K REC) | 7. CLIENT ID - 69ef852b-0fb3-4baa-8329-29ba4be371cb JOB GUID - e4c92cee-926b-4441-8c35-b8a7b6902804 (2K REC) | 8. CLIENT ID - c9099546-2737-4f7a-bd06-c4d4e8afbd1e JOB GUID - b515ad3b-0363-4ba2-ac38-93e66d360bdb (2K REC) | 9. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - bdaee162-824e-4cf9-931b-ffd63fdb697a (2K REC) | 9. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - d9cc727a-20ad-4951-8a76-0514da63b2d7 (2K REC)
STATUS | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:01 | 0:04 | 0:02 | 0:03 | 0:02 | 0:00 | 0:04
WEB JOB 1 Processing time | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 0:05 | 2:42 | 3:03 | 1:37 | 1:57 | 2:17 | 0:31
WEB JOB 2 Processing time | 0:21 | 0:22 | 0:20 | 0:20 | 0:20 | 0:20 | 0:20
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:04 | 0:01 | 0:02 | 0:00 | 0:03 | 0:01 | 0:01
WEB JOB 3 Processing time | 0:18 | 0:18 | 0:18 | 0:18 | 0:18 | 0:19 | 0:18
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 0:50 | 3:27 | 3:45 | 2:19 | 2:40 | 2:57 | 1:15
AVG. Time per input case | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
7 Records Triggered in Every 5 Mins | WAIT TIME 0 (START - WJ1) -- > | WEB JOB 1 Processing time | WAIT TIME 1 (WJ2 - WJ1) -- > | WEB JOB 2 Processing time | WAIT TIME 2 (WJ3 - WJ2) -- > | WEB JOB 3 Processing time | Total Processing Time | Time/Case Creation
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Iteration 7
Iteration 8
Iteration 9
Iteration 10
Iteration 11
Iteration 12

## R18_Test#2Baseline
FILES (20K REC) | 1. CLIENT ID - fce0bb0b-a37a-445b-8213-064bfeb7d1f4 JOB GUID - 973c6256-224a-4320-bfd3-992639013fb4 (2K REC) | 2. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 JOB GUID - 85ecfc2d-aff3-485f-bade-e71466837a84 (2K REC)
STATUS | Job successfully completed | Job successfully completed
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:04 | 0:03
WEB JOB 1 Processing time | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 0:05 | 0:24
WEB JOB 2 Processing time | 0:19 | 0:20
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:02 | 0:13
WEB JOB 3 Processing time | 0:31 | 0:30
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 1:00 | 1:30
AVG. Time per input case | 0:00 | 0:00
7 Records Triggered in Every 5 Mins | WAIT TIME 0 (START - WJ1) -- > | WEB JOB 1 Processing time | WAIT TIME 1 (WJ2 - WJ1) -- > | WEB JOB 2 Processing time | WAIT TIME 2 (WJ3 - WJ2) -- > | WEB JOB 3 Processing time | Total Processing Time | Time/Case Creation
Iteration 1 | 0:02 | 0:00 | 0:44 | 0:00 | 0:12 | 0:00 | 0:59 | 0:00
Iteration 2 | 0:03 | 0:00 | 0:05 | 0:00 | 0:27 | 0:00 | 0:36 | 0:00
Iteration 3 | 0:04 | 0:00 | 0:05 | 0:00 | 0:06 | 0:00 | 0:16 | 0:00
Iteration 4 | 0:05 | 0:00 | 0:09 | 0:00 | 0:13 | 0:00 | 0:27 | 0:00
Iteration 5 | 0:03 | 0:00 | 0:00 | 0:00 | 0:05 | 0:00 | 0:08 | 0:00
Iteration 6 | 0:03 | 0:00 | 0:05 | 0:00 | 0:05 | 0:00 | 0:13 | 0:00
Iteration 7 | 0:01 | 0:00 | 0:14 | 0:00 | 0:01 | 0:00 | 0:17 | 0:00
Iteration 8 | 0:05 | 0:00 | 0:04 | 0:00 | 0:13 | 0:00 | 0:22 | 0:00
Iteration 9 | 0:02 | 0:00 | 0:19 | 0:00 | 0:01 | 0:00 | 0:22 | 0:00
Iteration 10 | 0:01 | 0:00 | 0:09 | 0:00 | 0:01 | 0:00 | 0:11 | 0:00
Iteration 11 | 0:04 | 0:00 | 0:00 | 0:00 | 0:06 | 0:00 | 0:10 | 0:00
Iteration 12 | 0:01 | 0:00 | 0:04 | 0:00 | 0:01 | 0:00 | 0:06 | 0:00

## R18_Test#3_2217Run
FILES (4K REC) | 1. CLIENT ID - fce0bb0b-a37a-445b-8213-064bfeb7d1f4 JOB GUID - 6d89f667-a691-4f79-af05-ee20294d1612 (2K REC) | 2. CLIENT ID - 4ce60165-4071-4dc8-a29b-9f0ae382ed26 JOB GUID - 3263614f-2f8b-44d5-879c-2563a37243a9 (2K REC)
STATUS | Job Partially Succeeded (1983/2000) | Job Partially Succeeded (1967/2000)
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:01 | 0:00
WEB JOB 1 Processing time | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 1:02 | 0:05
WEB JOB 2 Processing time | 0:54 | 0:54
WAIT TIME 2 (WJ3 - WJ2) -- > | 2:02 | 0:01
WEB JOB 3 Processing time | 3:08 | 2:59
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 7:08 | 3:59
AVG. Time per input case | 0:00 | 0:00
7 Records Triggered in Every 5 Mins | WAIT TIME 0 (START - WJ1) -- > | WEB JOB 1 Processing time | WAIT TIME 1 (WJ2 - WJ1) -- > | WEB JOB 2 Processing time | WAIT TIME 2 (WJ3 - WJ2) -- > | WEB JOB 3 Processing time | Total Processing Time
Iteration 1 | 0:00 | 0:00 | 0:00 | 0:00 | 0:05 | 0:00 | 0:05
Iteration 2 | 0:02 | 0:00 | 0:36 | 0:00 | 6:09 | 0:01 | 6:49
Iteration 3 | 0:05 | 0:00 | 0:05 | 0:00 | 0:05 | 0:00 | 0:15
Iteration 4 | 0:01 | 0:00 | 0:25 | 0:00 | 6:12 | 0:01 | 6:41
Iteration 5 | 0:01 | 0:00 | 0:15 | 0:00 | 0:00 | 0:00 | 0:16
Iteration 6 | 0:02 | 0:00 | 0:31 | 0:00 | 6:11 | 0:01 | 6:45
Iteration 7 | 0:03 | 0:00 | 0:47 | 0:00 | 6:06 | 0:01 | 6:57
Iteration 8 | 0:04 | 0:00 | 0:00 | 0:00 | 0:05 | 0:00 | 0:09
Iteration 9 | 0:03 | 0:00 | 0:41 | 0:00 | 6:08 | 0:01 | 6:53
Iteration 10 | 0:01 | 0:00 | 0:20 | 0:00 | 6:14 | 0:02 | 6:37
Iteration 11 | 0:04 | 0:00 | 0:52 | 0:00 | 6:05 | 0:01 | 7:02
Iteration 12 | 0:01 | 0:00 | 0:05 | 0:00 | 0:05 | 0:00 | 0:11

## R18_Test#4_2217u
4K GDC
6437A817-06F5-4F95-AB7D-964CF90C3F4C c6cd0be3-f612-43a5-b223-7092eb119954 Job Successfully Completed
c9099546-2737-4f7a-bd06-c4d4e8afbd1e 83e036b1-4cfa-4b05-8822-ab48a402eeaf Job Partially Succeeded
aptured JOBGUID_0be9999c-e16c-4be0-be15-609f9adfdc4b,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_6040b67e-4b7c-4b61-8a74-232c93400a5c,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_7d521228-2b69-454a-87e8-5ca76f355dee,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_900057b1-f4fc-4d70-b34a-a6bc898d7d0a,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_9d2aeb28-961d-4bb2-9268-c9697401f106,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_a1497cde-c0b8-45f3-b898-922202edf36f,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_b3a69f5f-ff9e-4a4b-af33-5635b5c90ebf,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_c99fb5a8-1be6-4289-ba3e-976d074709b7,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_ca5d0784-5d77-400f-a51f-c56fbd3addc0,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_ca9bc260-d6e7-48ca-ad84-66e9dd8236dc,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_e1bdb88c-5bc5-4bd3-bdae-e4cd816b4141,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_f244ec8e-ef53-449e-966c-8cdde5aa784f,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
Captured JOBGUID_f9e48667-9bc5-409e-a983-79ab9eec9db1,Client_6437a817-06f5-4f95-ab7d-964cf90c3f4c
FILES (4K REC) | 1. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - c6cd0be3-f612-43a5-b223-7092eb119954 (2K REC) | 2. CLIENT ID - c9099546-2737-4f7a-bd06-c4d4e8afbd1e JOB GUID - 83e036b1-4cfa-4b05-8822-ab48a402eeaf (2K REC)
STATUS | Job successfully completed | Job Partially Succeeded (1999/2000)
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:02 | 0:01
WEB JOB 1 Processing time | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 0:05 | 0:58
WEB JOB 2 Processing time | 0:51 | 0:46
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:05 | 0:13
WEB JOB 3 Processing time | 0:55 | 0:37
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 1:58 | 2:34
AVG. Time per input case | 0:00 | 0:00
7 Records Triggered in Every 5 Mins | WAIT TIME 0 (START - WJ1) -- > | WEB JOB 1 Processing time | WAIT TIME 1 (WJ2 - WJ1) -- > | WEB JOB 2 Processing time | WAIT TIME 2 (WJ3 - WJ2) -- > | WEB JOB 3 Processing time | Total Processing Time
Iteration 1 | 0:04 | 0:00 | 0:37 | 0:00 | 0:03 | 0:00 | 0:44
Iteration 2 | 0:01 | 0:00 | 0:05 | 0:00 | 0:05 | 0:00 | 0:12
Iteration 3 | 0:01 | 0:00 | 0:12 | 0:00 | 0:04 | 0:01 | 0:18
Iteration 4 | 0:04 | 0:00 | 0:42 | 0:00 | 0:02 | 0:00 | 0:50
Iteration 5 | 0:02 | 0:00 | 0:17 | 0:00 | 0:04 | 0:00 | 0:23
Iteration 6 | 0:03 | 0:00 | 0:27 | 0:00 | 0:03 | 0:00 | 0:33
Iteration 7 | 0:01 | 0:00 | 0:06 | 0:00 | 0:05 | 0:00 | 0:13
Iteration 8 | 0:03 | 0:00 | 0:32 | 0:00 | 0:03 | 0:00 | 0:39
Iteration 9 | 0:01 | 0:00 | 0:05 | 0:00 | 0:05 | 0:00 | 0:11
Iteration 10 | 0:05 | 0:00 | 0:48 | 0:00 | 0:02 | 0:00 | 0:55
Iteration 11 | 0:00 | 0:00 | 1:44 | 0:00 | 0:12 | 0:00 | 1:57
Iteration 12 | 0:01 | 0:00 | 0:00 | 0:00 | 0:05 | 0:00 | 0:06

## R18_Test#5_GDC1.2_GB_2217u
FILES (4K REC) | 1. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - 458f5eeb-ddfa-42ec-978e-a7ab7d125b4b (2K REC) | 2. CLIENT ID - c9099546-2737-4f7a-bd06-c4d4e8afbd1e JOB GUID - 83e036b1-4cfa-4b05-8822-ab48a402eeaf (2K REC)
STATUS | Job Failed | Job Failed
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:03 | 0:01
WEB JOB 1 Processing time | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 0:28 | 0:05
WEB JOB 2 Processing time | 0:25 | 0:23
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:19 | 0:03
WEB JOB 3 Processing time | 0:41 | 0:41
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 1:58 | 1:12
AVG. Time per input case | 0:00 | 0:00

## R18.0.1_Test#1_GDC1.3_GB_2217u
FILES (4K REC) | 1. CLIENT ID - 6437A817-06F5-4F95-AB7D-964CF90C3F4C JOB GUID - 458f5eeb-ddfa-42ec-978e-a7ab7d125b4b (2K REC) | 2. CLIENT ID - c9099546-2737-4f7a-bd06-c4d4e8afbd1e JOB GUID - 83e036b1-4cfa-4b05-8822-ab48a402eeaf (2K REC)
STATUS | Job successfully completed | Job successfully completed
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 0:01 | 0:01
WEB JOB 1 Processing time | 0:00 | 0:00
WAIT TIME 1 (WJ2 - WJ1) -- > | 0:05 | 0:25
WEB JOB 2 Processing time | 0:25 | 0:23
WAIT TIME 2 (WJ3 - WJ2) -- > | 0:05 | 0:09
WEB JOB 3 Processing time | 0:27 | 0:27
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 1:02 | 1:25
AVG. Time per input case | 0:00 | 0:00

## Auto_16Mar2026_1943
FILES (4000 REC) | JOB GUID - 3f7e7814-fd0a-4b50-857c-86179460ee8d (2000 REC) | JOB GUID - 0c2ffe6e-6e94-4dc8-83a0-8e093a32e55d (2000 REC) | JOB GUID - 56e75e34-ac5e-4a3e-8a42-42f32cf82b95 (7 REC) | JOB GUID - cbb6b2d9-192f-4e01-ac2d-e40d36bef202 (7 REC) | JOB GUID - 50ce2d2e-8f12-4c3b-b06d-16e9bd2758ce (7 REC) | JOB GUID - bf342ebe-f892-4aac-9252-d0444071cb80 (7 REC) | JOB GUID - 92644c7b-7924-4ea0-80b9-03ab17bc60a9 (7 REC) | JOB GUID - 8eb6bdb5-9ed6-48db-88d3-e3e6b530cc29 (7 REC) | JOB GUID - 0ba6621b-ffbe-4f74-8e98-38fe2fc04eb2 (7 REC) | JOB GUID - e26a595f-abbf-4076-985e-7b3306935d55 (7 REC) | JOB GUID - 6fc55bff-fef0-49e5-9020-195cc7c99aaa (7 REC) | JOB GUID - b614ff02-d2c9-4056-9acd-8bcbbf0474d2 (7 REC)
STATUS | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed | Job successfully completed
CREATE JOB >> | TRIGGER
WAIT TIME 0 (START - WJ1) -- > | 00:02:50.637000 | 00:01:12.674000 | 00:00:50.412999 | 00:03:29.729999 | 00:03:06.456999 | 00:01:33.346999 | 00:04:40.596000 | 00:02:18.396999 | 00:01:11.944000 | 00:04:18.244000 | 00:03:53.296999 | 00:00:28.437000
WEB JOB 1 Processing time | 00:00:08.452999 | 00:00:05.599999 | 00:00:01.649999 | 00:00:01.199999 | 00:00:05.115999 | 00:00:01.227000 | 00:00:00.854000 | 00:00:00.933000 | 00:00:00.926000 | 00:00:00.956000 | 00:00:05.703000 | 00:00:00.990000
WAIT TIME 1 (WJ2 - WJ1) -- > | 00:04:58.247000 | 00:45:26.670000 | 00:55:39.804000 | 00:00:09.984000 | 00:04:56.689999 | 01:05:23.150000 | 00:36:10.163000 | 01:15:06.806999 | 01:00:32.447000 | 00:31:18.567000 | 00:04:58.452999 | 00:50:48.817000
WEB JOB 2 Processing time | 00:40:32.726999 | 00:39:14.460000 | 00:00:07.043000 | 00:00:01.786000 | 00:00:04.564000 | 00:00:07.642999 | 00:00:07.160000 | 00:00:06.423000 | 00:00:06.932999 | 00:00:07.743000 | 00:00:05.919999 | 00:00:08.382999
WAIT TIME 2 (WJ3 - WJ2) -- > | 00:04:20.512999 | 00:01:51.060000 | 00:30:27.977000 | 00:05:09.600000 | 00:04:53.872999 | 00:30:25.529999 | 00:30:24.442999 | 00:30:26.207000 | 00:30:26.477000 | 00:30:23.723999 | 00:04:51.074000 | 00:30:27.707000
WEB JOB 3 Processing time | 00:36:44.637000 | 00:28:44.395999 | 00:00:09.012999 | 00:00:10.173999 | 00:00:10.132999 | 00:00:08.856999 | 00:00:07.847000 | 00:00:07.963000 | 00:00:09.490000 | 00:00:09.369999 | 00:00:20.666000 | 00:00:07.996000
WAIT TIME 3 (WJ4 - WJ3) -- >
RETRY JOB Processing time
TOTAL PROCESSING TIME (hh:mm:ss.000) | 01:29:35.213999 | 01:56:34.859999 | 01:27:15.899999 | 00:09:02.474000 | 00:13:16.832999 | 01:37:39.753999 | 01:11:31.063000 | 01:48:06.729999 | 01:32:28.216999 | 01:06:18.603999 | 00:14:15.113000 | 01:22:02.329999
AVG. Time per input case | 00:00:02.687606 | 00:00:03.497430 | 00:12:27.985714 | 00:01:17.496285 | 00:01:53.833286 | 00:13:57.107713 | 00:10:13.009000 | 00:15:26.675713 | 00:13:12.602429 | 00:09:28.371999 | 00:02:02.159000 | 00:11:43.190000